# PROJECT CHARTER

## Real-Time Multimodal Financial Fraud Detection System

### Project Sponsor

Module Leader — Jing Wang

### Project Overview

Financial fraud is increasing in volume and complexity, particularly in card-not-present payments and digital banking environments. Traditional rule-based systems struggle to detect evolving fraud patterns, suffer from high false-positive rates, and create customer friction.

This project develops a real-time hybrid fraud detection system combining:

- Supervised machine learning using the IEEE-CIS Fraud Detection dataset,

- Unsupervised anomaly detection,

- Computer Vision for document/ID forgery detection,

- Natural Language Processing for detecting phishing or suspicious text messages.

The system includes a FastAPI backend, real-time alerting, and a React dashboard.

### Stakeholders

| Stakeholder | Role / Interest |
| --- | --- |
| Project Sponsor | Oversees academic alignment, approves deliverables |
| Module Tutors | Provide formative feedback (Weeks 4, 7, 10) |
| Project Team (5 Members) | Develop full pipeline, produce code, PM artefacts, documentation |
| End-user (Fraud Analyst Persona) | Uses dashboard to monitor suspicious transactions in real-time |
| Examiners | Assess technical implementation, evaluation, ethics, and project management |

### Scope (MoSCoW Analysis)

#### MUST Have

- Tabular fraud detection using IEEE-CIS dataset

- Time-based data split + feature engineering

- Supervised model (XGBoost/LightGBM)

- Anomaly detection model (Isolation Forest / Autoencoder)

- FastAPI backend for model inference

- React dashboard with real-time alerts (WebSockets)

- Evaluation using PR-AUC, MCC, Calibration, Cost Analysis

- Ethical analysis & responsible AI section

#### SHOULD Have

- Computer Vision model for document/ID fraud

- NLP phishing/text classifier

- SHAP explainability on fraud alerts

- Basic database logging (SQLite/PostgreSQL)

#### COULD Have

- Drift detection visualisation

- Threshold tuning interface

- Additional graphs & analytics

#### WON’T Have (This semester)

- Production-level cloud deployment

- Full multimodal unified model (cross-modal training)

- Integration with financial APIs or real bank data (security constraints)

### Project Goals & SMART Objectives

### Goal 1 – Build a real-time fraud detection system

#### Objective 1.1

Specific: Train supervised and anomaly models using IEEE-CIS data.
Measurable: Achieve ≥ 0.90 PR-AUC on validation.
Achievable: Based on known benchmarks for this dataset.
Relevant: Supports fraud detection effectiveness.
Time-bound: Complete by Week 7

### Goal 2 – Enable real-time detection and alerting

Objective 2.1: Implement FastAPI backend with <300ms local inference latency 
Objective 2.2: Deliver WebSocket live alert stream on dashboard by Week 9.

### Goal 3 – Deliver multimodal fraud support (CV + NLP)

Objective 3.1: Train a CNN for detecting manipulated images by Week 6.
Objective 3.2: Fine-tune a phishing classifier using BERT/DistilBERT by Week 6.

### Goal 4 – Complete evaluation and ethical analysis

Objective 4.1: Produce evaluation with PR-AUC, MCC, calibration curves, cost metrics by Week 10.
Objective 4.2: Complete ethical analysis (bias, fairness, SCA/PSD2 compliance) by Week 11.

### Success Metrics

### Technical Metrics

- PR-AUC ≥ 0.90 (tabular model)

- MCC > 0.50

- Brier Score improvement after calibration

- Latency: <300 ms per transaction (demo environment)

- Dashboard streaming reliability: >95% messages delivered

### Project Delivery Metrics

- Weekly GitHub commits from all 5 members (required by module)

- Updated GitHub Project Board (issues → done) each week

- Demo-ready system by Week 11 (live presentation requirement)

## Assumptions & Constraints

### Assumptions

- IEEE-CIS dataset is sufficient for training fraud models

- CV & NLP datasets are available publicly

- All team members contribute weekly to GitHub (required for engagement tracking)

- Local machines can train and serve models with moderate batch sizes

### Constraints

- Strict 12-week project timeline from Week 1–12

- Live demo requirement: No screenshots allowed; must run real code in Week 11/12

- Maximum 4 pages for final report (excluding appendix)

- Ethical and responsible AI discussion is mandatory

### Project Milestones

| Week | Milestone | Related Deliverables |
| --- | --- | --- |
| 1–2 | Project Charter | Charter document |
| 3–4 | Gantt + RACI + Risk Register | PM artefacts |
| 4–6 | Dataset acquisition + preprocessing | IEEE-CIS cleaning + CV + NLP datasets |
| 5–7 | ML model development | Supervised + anomaly models |
| 6–7 | CV & NLP models complete | CNN + BERT models |
| 7–9 | Backend development | FastAPI + model endpoints |
| 8–10 | Frontend dashboard | Live alerts + visualisations |
| 9–10 | Evaluation | Metrics, calibration, cost curves |
| 10–11 | Ethics & critical analysis | LO4 compliance |
| 11–12 | Final demo + Submission | Pitch + report + code |

### Roles & Responsibilities

- Jibola Johnson Odekunle (Product + CV/NLP): Documentation, CV module, NLP module, report, PPT

- Aniruddha Ashok Patil (Data Engineer): IEEE-CIS preprocessing, merging, feature engineering

- Gaurav Sanjay Karnavar (ML Engineer): Model training, anomaly detection, calibration, evaluation

- Anderson Lucas Cachinavissa Aurelio (Backend Engineer): FastAPI, model endpoints, WebSockets, DB

- Onyinye Eugenia Asadu (Frontend Developer): React dashboard, charts, alert stream

### Risks & Mitigation Strategy

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Dataset too large → slow training | Medium | Medium | Use downsampled dev set first; optimize features |
| CV/NLP data unavailable | High | Low | Use open-source forgery + phishing datasets |
| GitHub inactivity (penalises marks) | High | Medium | Weekly internal deadlines; rotate reviewer |
| Model underperformance | High | Medium | Hyperparameter tuning + calibration |
| Backend latency too high | Medium | Medium | Use optimized models; batch inference |
| Demo failure | High | Low | Rehearse demo; fallback local-only mode |
| Ethical/fairness oversight | High | Medium | Dedicated bias analysis |

### Approval / Signoff

#### Approval Signature (Sponsor): _______________________
Date: _______________________